Benchmark Research and Output Verification

Addendum to the AfCEN CDE Platform PRD. Requirements FR-13 to FR-24.

Internal document. Not for circulation to bidders or the Developer's partners. Section 10 covers disclosure.

| Field | Detail |
| --- | --- |
| Document | Benchmark Research and Output Verification, v0.1 draft |
| Owner | Dennis Nderitu, AfCEN |
| Extends | AfCEN CDE Platform PRD. Continues the FR numbering from FR-12. |
| Depends on | FS Deliverable Review Standard, which supplies the section-level acceptance criteria this capability automates. |
| Purpose | Give the platform the ability to research benchmarks from public sources, replicate the analysis with the same tool class as the Consultant, and verify that outputs sit inside a declared accuracy range. |
| Status | Draft for internal build use. Open items in Section 11. |

# 1  What this adds, and why it matters

The Platform PRD gives FR-3 a benchmark library and FR-4 a threshold check. The FS Review Standard supplies the rulebook. All three still assume that someone has put credible reference values into the library by hand. On present evidence that library is one project, at 2020 prices, with a flat per-km rate. Thresholds set on that data would produce noise, and the flag-accepted ratio is the metric the platform is judged on.

This addendum closes that gap with three capabilities. First, the platform researches benchmarks from public sources for each input and assumption, and normalises them to a common basis. Second, it re-runs the analysis with the same class of tool the Consultant used, so the check is against a computed result and not only a reference number. Third, it verifies that each output sits inside a declared accuracy range, using a recognised classification rather than an in-house rule.

The boundaries in the Platform PRD do not move. The checks stay advisory, the Consultant remains the sole signatory under TOR Section 8.3, and the PM team remains the sole approval authority. A replication that disagrees with the Consultant raises a question for the PM team. It never becomes the answer.

# 2  The research problem is normalisation, not harvesting

Public transmission cost data exists but is not comparable as published. Scope definitions differ, price years differ, currencies differ, and terrain and voltage drive costs more than any average conveys. ESMAP makes this point directly in its April 2026 technical report: cost categories are not standardised across the literature, which leaves published breakdowns hard to compare and trends uncertain. Fichtner's cost tool, built on 68 projects of which 78 percent are African, concludes that comparing many projects gives no usable estimate unless project specifics are accounted for.

A worked example makes the point concretely, using the reference PFS rate of 153,846 USD per km for 132 kV double circuit in Uganda.

| Step | Result | Consequence |
| --- | --- | --- |
| Naive check against ACER Europe, 0.318 M/km | PFS rate is 2.07 times lower | False Material flag |
| Naive check against NCEP US, 0.421 M/km | PFS rate is 2.74 times lower | False Material flag |
| Normalised: apply the ESMAP finding that World Bank projects in developing markets run 1.56 to 4.35 times below developed-market benchmarks | Developing-market equivalent band of 0.073 to 0.270 M/km in 2010 values, about 0.093 to 0.343 M/km once escalated | PFS rate of 0.154 sits inside the band. No flag. |
| Structural check on how the rate was built | One flat rate applied across the 123, 141 and 152 km options | Advisory flag: the rate is plausible in aggregate but is not terrain-differentiated |

Read the third and fourth rows together. Without normalisation the platform would have raised two confident, wrong flags against a figure that is defensible. That is the fastest way to lose the PM team. With normalisation it raises no cost flag, and instead raises the flag that is actually true: the estimate ignores terrain on a corridor whose Mt. Elgon foothills section is the part that drives tower cost. ESMAP's cost-driver review quantifies exactly that premium: about 15 percent in mountainous areas, up to 78 percent on high slopes, 10 percent for difficult access, 7 percent for soft-soil foundations and 35 percent for piled foundations, against a 10 percent discount for lines over 100 km.

The escalation factor above is a placeholder. FR-15 requires a named index, because the answer moves with it.

# 3  Source register (FR-13)

The platform researches against a tiered register. Tier 1 is structured, dated and licensed. Tier 2 is credible but needs normalisation. Tier 3 is project-specific and must be treated as a single observation.

| Tier | Source | What it gives | Licence |
| --- | --- | --- | --- |
| 1 | ESMAP Transmission Cost Database and technical report, April 2026 | 74 World Bank projects, 2000 to 2024, USD 21bn, mined from 469. CAPEX per km by region and voltage, O&M rates, discount rates, actual against appraisal cost, delay causes, and the LCOT framework. | CC BY 3.0 IGO. Adaptation and commercial use permitted with attribution. Confirm before build. |
| 1 | MISO Transmission Cost Estimation Guide (MTEP series) | Component unit costs: line cost by voltage, substation bay cost, shunt reactor cost per Mvar. Updated annually. | US-based. Confirm licence and apply location adjustment. |
| 1 | ACER Unit Investment Cost indicators | 99 European overhead-line investments, 2012 to 2022, by voltage band. | Confirm. |
| 2 | Fichtner (2016) cost tool | 68 projects, 78 percent African. Base cost plus line configuration, line location and project location factors. | Confirm. |
| 2 | Pletka (2014) / Black and Veatch for WECC | Base cost with adjustment factors for conductor, tower design and voltage class. | Confirm. |
| 2 | World Bank Business Ready, Logistics Performance Index, Worldwide Governance Indicators | Project-location drivers: regulatory burden, logistics, governance. These are the country-risk multipliers. | Open. |
| 2 | Regulator filings and utility annual reports (ERA, UETCL, and regional equivalents) | Tariff, wheeling, RAB and actual outturn costs in-country. | Public. |
| 2 | Procurement notices and contract awards (World Bank, AfDB, national portals) | Awarded prices, which are outturn rather than estimate. | Public. |
| 3 | Prior PFS, FS and appraisal documents for the corridor | Project-specific precedent. | Project data. Developer's property per TOR Section 14. |

The ESMAP entry is the single most valuable item on this list, and its licence is the reason. It is published under a Creative Commons licence that permits adaptation, including for commercial purposes, with attribution. That means the benchmark library can be built on it lawfully rather than assembled from scraped fragments of uncertain provenance. It is also the right shape: it reports ranges, it separates region and voltage, and it is drawn from appraisal and completion documents rather than from marketing material.

# 4  Functional requirements: benchmark research

| ID | Requirement | Priority |
| --- | --- | --- |
| FR-13 | The system shall maintain a tiered source register as in Section 3, each source carrying its publisher, vintage, coverage, geography and licence, and shall re-check each source for a newer edition on a defined cycle. | P1 |
| FR-14 | The system shall extract benchmark records from public sources into structured entries, each carrying a resolvable citation to the page or table it came from. An entry without a resolvable citation shall be rejected, not stored with a lower confidence. | P1 |
| FR-15 | The system shall normalise every entry to a declared common basis before use: scope definition, currency, price year and named escalation index, voltage, circuit count, conductor class, terrain class, region, and whether the figure is an estimate or an outturn. | P1 |
| FR-16 | Every benchmark shall be expressed as a range with a sample count, never as a single average. ESMAP records minimum-to-maximum ratios of 2 to 3 across its sample and recommends ranges over averages for exactly this reason. | P1 |
| FR-17 | The system shall apply the cost-driver factors from the register to adjust a benchmark to the project's own configuration, location and terrain before comparison, and shall show the adjustment chain alongside the flag. | P1 |
| FR-18 | Where a benchmark has fewer than three independent sources after normalisation, a deviation against it shall raise an Advisory flag at most, never Material. | P0 |

# 5  Functional requirements: methodology and tool replication

This is what turns a reference-value check into a real second opinion, and it is the dual-track idea from the Uganda development ToR expressed as a product feature.

| ID | Requirement | Priority |
| --- | --- | --- |
| FR-19 | The system shall re-run the analysis behind a submitted deliverable using the same class of tool as the Consultant: sectoral end-use demand modelling (MAED class), least-cost capacity expansion (OSeMOSYS class), network studies (PSS/E or DIgSILENT PowerFactory, matching the utility's standard), and line design and spotting (PLS-CADD class). | P2 |
| FR-20 | The system shall check methodology conformance separately from result conformance: whether the required study was performed at all, against the applicable grid code and the FS Review Standard, before asking whether its answer matches. | P1 |
| FR-21 | Replication inputs shall be pinned and versioned so that any variance can be attributed to an input difference, a method difference or a genuine disagreement. An unattributable variance shall not be raised as a flag. | P2 |
| FR-22 | Replication output shall be a variance report readable without either track's authors present, covering cost, route, rating, compensation, schedule and readiness. | P2 |

A caution worth writing into the build. FR-19 is the most expensive requirement in the whole PRD and the easiest to oversell. Re-running a PSS/E case needs the utility's network model, which the platform may not hold, and re-running PLS-CADD needs the survey the Consultant commissioned. Where the input is absent, the honest behaviour is to report that the check could not be run, not to substitute a public proxy and present the result as a replication. This is the same failure mode the Review Standard blocks elsewhere.

# 6  Functional requirements: accuracy-range verification

Accuracy needs a recognised yardstick rather than an in-house one. AACE International's cost estimate classification is the standard reference, in 18R-97 for process industries and 98R-18 for transport infrastructure, and it ties the credible accuracy range to how much of the project is actually defined.

| Class | Usage | Definition | Accuracy range | Stage |
| --- | --- | --- | --- | --- |
| Class 5 | Concept screening | 0 to 2% | -50% to +100% | Pre-feasibility |
| Class 4 | Study or feasibility | 1 to 15% | -30% to +50% | Feasibility |
| Class 3 | Budget authorisation | 10 to 40% | -20% to +30% | Post-FS |
| Class 2 | Control or tender | 30 to 75% | -15% to +20% | Tender |
| Class 1 | Check estimate | 65 to 100% | -10% to +15% | Execution |

| ID | Requirement | Priority |
| --- | --- | --- |
| FR-23 | Each cost deliverable shall declare its estimate class. The system shall check the declared class against the deliverable maturity actually evidenced, and flag a class claimed but not supported. | P1 |
| FR-24 | The system shall check that a stated accuracy range was derived from project risk analysis rather than copied from the classification table, and shall flag a symmetric band as unlikely to be risk-derived. | P1 |

## 6.1  Why FR-24 is not pedantry

AACE is explicit that the accuracy range should be established by risk analysis of the specific project and should never be pre-determined, and that roughly 80 percent of projects should fall inside the range if contingency has been handled properly. A range is therefore a claim about risk, not a label.

The check catches this on our own work, which is the fairest test of it. The Ghanzi-Gobabis pre-feasibility reports a capital cost of USD 432 million at plus or minus 35 percent. No AACE class has a symmetric band. Class 4, the feasibility class, runs from minus 30 to plus 50 percent, skewed positive because that is how project cost risk actually behaves. A symmetric plus or minus 35 percent is a reasonable-sounding number that does not match any class shape, which is the signature of a range asserted rather than derived. ESMAP's own sample supports the skew: close to 70 percent of the 74 projects were delayed, mainly on procurement or land, though about half still closed under their appraisal estimate.

The requirement that follows is simple. A consultant submitting an FS cost estimate declares a class, evidences the definition level behind it, and derives the range from risk analysis. The platform checks all three and flags the gap. This is a check the PM team can defend to a lender in one sentence.

# 7  What gets verified, by output type

| Output | Benchmark source | Replication | In-range test |
| --- | --- | --- | --- |
| CAPEX per km | ESMAP by region and voltage, normalised, plus driver factors | Component build-up from surveyed quantities | AACE class band |
| Substation and bay | MISO component guide, location-adjusted | Bay count from single-line diagram | AACE class band |
| Reactive compensation | MISO cost per Mvar | Network study result | Against computed Mvar need |
| O&M rate | ESMAP: 2 to 3% of capex in the sample, against 5 to 10% in the wider literature | Not replicated | Range test |
| Discount rate / WACC | ESMAP: clusters 6 to 12% with concessional finance | Financial model | Range test |
| Wheeling / tariff | ESMAP LCOT framework as a reference where regulated tariffs are absent or unreliable | LCOT computation | Range test |
| Demand forecast | National plans, utility outturn, regional plans | MAED-class re-run | Scenario envelope |
| Load flow and N-1 | Grid code limits | PSS/E or PowerFactory re-run | Pass or fail against code |
| Schedule | ESMAP: about 70% of projects delayed, mainly procurement or land | Not replicated | Optimism-bias test |
| Contingency | AACE and ESMAP outturn against appraisal | Risk analysis | Class-consistent |

The LCOT row is worth attention beyond this project. ESMAP positions LCOT as a reference for wheeling charges where an official tariff is missing or inconsistent, which is precisely the position on cross-border links and a live question for the Uganda IPT tariff work.

# 8  Demo implications

The demo scope in the Platform PRD asks for one real benchmark flag with the source shown. This addendum changes what the strongest demo is.

- The arithmetic flag from the FS Review Standard stays the opener. It is real, verifiable and immediate.

- The stronger second beat is the normalisation sequence in Section 2: show the naive check raising two confident false flags, then show normalisation clearing the figure and raising the terrain flag instead. That demonstrates judgement, which is what a PM audience is actually buying.

- The accuracy-class check in Section 6.1 is the third beat, and it is more persuasive run against our own pre-feasibility than against a consultant's work.

This also gives an honest answer to the current-state question flagged in the Budget Justification note. The platform does not have to claim a trained model. It can show a real public dataset, a real normalisation chain and a real check, all of which exist today.

# 9  Risks

| Risk | Why it matters here | Mitigation |
| --- | --- | --- |
| False precision | A normalised benchmark carries an implied confidence its sources do not support. | FR-16 ranges with sample counts. FR-18 confidence floor. |
| Scope mismatch | Per-km figures include different things. ESMAP finds no standard cost categories across the literature. | FR-15 declared scope definition per entry. |
| Fabricated or drifting citations | A research agent that invents a plausible source is worse than no library, and would end the platform's credibility with a lender in one meeting. | FR-14 rejects any entry without a resolvable citation. Spot-audit before launch. |
| Replication oversold | A public-proxy run presented as a replication of the Consultant's model. | FR-19 and the caution in Section 5. Report the gap instead. |
| Stale rates | 2020 rates checked against 2026 submissions. | FR-15 named escalation index. |
| Benchmark used as a decision | A flag treated as a finding. | Unchanged boundaries. FR-5 stands. |

# 10  Disclosure

The split from the FS Review Standard carries over. The source register in Section 3 is drawn from public documents, so its existence is not sensitive, but the normalised library, the driver factors as configured, and the confidence fields are AfCEN's asset and stay internal. The accumulation of consultant-published figures into the library remains FR-11 and remains internal.

One point to settle deliberately. A capability that researches public benchmarks is easy to describe externally and reflects well on the Developer: it says the PM team checks submissions against the best available public evidence. That is a materially easier story to tell a sponsor than a learning loop is, and it may be the right thing to lead with in the JDA discussions.

# 11  Open questions

| # | Question | Recommendation |
| --- | --- | --- |
| 1 | Which escalation index applies to transmission capex in East Africa? | Needs an owner. Nothing in the library is usable at a Material threshold until it is set. |
| 2 | Is the ESMAP database available as data, or only as the report? | Ask ESMAP directly. The report says the database is Excel-based, and the licence permits adaptation. |
| 3 | Does the platform hold the utility network case needed for FR-19? | Likely not at launch. Scope FR-19 to Phase C and say so. |
| 4 | Who owns the normalisation schema in FR-15? | It is the core IP of this capability. Treat it as such in the IP split with the Developer. |
| 5 | Does the Consultant declare an AACE class in its deliverables today? | If the TOR does not require it, FR-23 has nothing to check. Consider it for the PM Strategy document. |
| 6 | MISO and ACER licence terms for commercial reuse. | Confirm before the library ships. |